## 2022 Bond
| 1 |  | 2 |  | 3 |  | 4 | 5 | 6
Proposed 2022 Bond Budget-to Actual (a/o January 31, 2026)
|  | CONSTRUCTION COSTS |  |  | TOTALS TO DATE
|  | Projects | Initial | Budget Amendments | Budget a/o December 31, 2025 | Budget a/o January 31, 2026 | Actuals | Commitments | Balance
Proposition A
1 |  | Modernization Full Projects:
2 |  | Allison Elementary | 56093606 | 0 | 58798343 | 58798343 | 27081062 | 28692847 | 3024434
3 |  | Andrews Elementary | 38685616 | 0 | 28747721 | 28747721 | 1331094 | 3348891 | 24067736
4 |  | Barrington Elementary | 38686157 | 0 | 30046079 | 30046079 | 3378326 | 1604509 | 25063244
5 |  | Burnet Middle School | 157515834 | 0 | 150538120 | 150538120 | 19080638 | 117503596 | 13953886
6 |  | Full Modernization Portable Rental | 0 | -942394 | 1952116 | 1009722 | 994231 | 0 | 15491
7 |  | Harris Elementary | 56093690 | 0 | 55118335 | 55118335 | 47643396 | 5679917 | 1795022
8 |  | Houston Elementary | 56094328 | 0 | 61925092 | 61925092 | 33416169 | 23958484 | 4550439
9 |  | Langford Elementary | 39653095 | 941231 | 66567247 | 67508478 | 19274408 | 40767250 | 7466820
10 |  | Linder Elementary | 56093739 | 0 | 69513403 | 69513403 | 45824568 | 22000470 | 1688365
11 |  | Nelson Bus Terminal | 18584000 | 0 | 14011469 | 14011469 | 206952 | 859997 | 12944520
12 |  | Oak Springs Elementary | 47499918 | 0 | 58226376 | 58226376 | 11074006 | 38387887 | 8764483
13 |  | Pecan Springs Elementary | 47499812 | 5985 | 57139040 | 57145025 | 32745821 | 21673194 | 2726010
14 |  | Sadler Means YWLA | 101916842 | -5000 | 109575501 | 109570501 | 47350098 | 52494556 | 9725847
15 |  | Sims Facility | 0 | 0 | 5610891 | 5610891 | 5159691 | 296089 | 155111
16 |  | Travis Early College High School | 251455962 | 0 | 209255751 | 209255751 | 74580589 | 126825846 | 7849316
17 |  | Wooldridge Elementary | 38686155 | 0 | 30960101 | 30960101 | 3907831 | 2381284 | 24670986
18 |  | Wooten Elementary | 39653337 | 178 | 58968235 | 58968413 | 52225845 | 6098736 | 643832
19 |  | Subtotal Modernization Full Projects: | 1044212091 | 0 | 1066953820 | 1066953820 | 425274725 | 492573553 | 149105542
20 |  | Modernization Phased Projects:
21 |  | Anderson High School | 45576452 | 0 | 31888368 | 31888368 | 6285889 | 20542750 | 5059729
22 |  | Austin High School | 39999647 | 0 | 27668470 | 27668470 | 2491771 | 4779120 | 20397579
23 |  | Crockett Early College High School | 65345218 | 0 | 51089623 | 51089623 | 6159229 | 15180398 | 29749996
24 |  | Dobie Middle School | 36186775 | 0 | 27562157 | 27562157 | 4510056 | 17177396 | 5874705
25 |  | Hill Elementary | 29999621 | 0 | 22205487 | 22205487 | 191538 | 3412941 | 18601008
26 |  | LBJ Early College High School | 115685422 | 0 | 84387486 | 84387486 | 29181399 | 46736283 | 8469804
27 |  | Martin Middle School | 60999930 | 0 | 45964067 | 45964067 | 11070704 | 25453840 | 9439523
28 |  | McCallum High School | 64999525 | 0 | 46641997 | 46641997 | 8085683 | 31186683 | 7369631
29 |  | Navarro Early College High School | 60000017 | 0 | 42864166 | 42864166 | 5578996 | 31179741 | 6105429
30 |  | Northeast ECHS / International High School | 116686347 | 0 | 85757992 | 85757992 | 11687157 | 61944819 | 12126016
31 |  | O Henry Middle School | 61000226 | 0 | 45952579 | 45952579 | 844368 | 2254256 | 42853955
32 |  | Phased Modernization Portable Rental | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 |  | Subtotal Modernization Phased Projects: | 696479180 | 0 | 511982392 | 511982392 | 86086790 | 259848227 | 166047375
34 |  | Subtotal Modernization Projects | 1740691271 | 0 | 1578936212 | 1578936212 | 511361515 | 752421780 | 315152917
35 |  | Targeted Projects:
36 |  | Mental Health Center:
37 |  | Brown Elementary | 130306 | 0 | 118631 | 118631 | 0 | 18500 | 100131
38 |  | Eastside Early College High School | 8988857 | 0 | 0 | 0 | 0 | 0 | 0
39 |  | Govalle Elementary | 132103 | 0 | 120323 | 120323 | 0 | 0 | 120323
40 |  | Norman-Sims Elementary | 131639 | 0 | 119886 | 119886 | 0 | 0 | 119886
41 |  | Subtotal Mental Health Center: | 9382905 | 0 | 358840 | 358840 | 0 | 18500 | 340340
42 |  | Open Concept:
43 |  | Cook Elementary | 14507425 | 0 | 15041415 | 15041415 | 13794565 | 1151689 | 95161
44 |  | Oak Hill Elementary | 18375508 | 0 | 22976577 | 22976577 | 20217543 | 1989890 | 769144
45 |  | Odom Elementary | 9188130 | 0 | 8894187 | 8894187 | 7829614 | 805194 | 259379
46 |  | Williams Elementary | 16925019 | 0 | 18725410 | 18725410 | 16827907 | 1626109 | 271394
47 |  | Subtotal Open Concept: | 58996082 | 0 | 65637589 | 65637589 | 58669629 | 5572882 | 1395078
48 |  | Renovations without Secure Vestibule:
49 |  | Bear Creek Elementary | 13999757 | 0 | 10617625 | 10617625 | 30909 | 0 | 10586716
50 |  | Eastside Early College High School | - | 0 | 6987758 | 6987758 | 161763 | 513239 | 6312756
51 |  | Liberal Arts and Science Academy | 28398484 | 0 | 19027073 | 19027073 | 1327846 | 139347 | 17559880
52 |  | Murchison Middle School | 3193377 | 0 | 2117232 | 2117232 | 166737 | 4450 | 1946045
53 |  | Saegert Bus Terminal | 1000000 | 0 | 945440 | 945440 | 0 | 0 | 945440
54 |  | Sanchez Elementary | 591738 | 0 | 505301 | 505301 | 0 | 0 | 505301
55 |  | Subtotal Renovations without Secure Vestibule: | 47183356 | 0 | 40200429 | 40200429 | 1687255 | 657036 | 37856138
56 |  | Secure Vestibule and Other Targeted Work:
57 |  | Akins Early College High School | 15742434 | 0 | 11040860 | 11040860 | 2796012 | 6229544 | 2015304
58 |  | Anita Coy (ALC) | 621959 | 0 | 0 | 0 | 0 | 0 | 0
59 |  | Bailey Middle School | 7461109 | 0 | 5840245 | 5840245 | 987725 | 3762750 | 1089770
60 |  | Baldwin Elementary | 2504961 | 0 | 1374799 | 1374799 | 744903 | 24283 | 605613
61 |  | Baranoff Elementary | 5063700 | 0 | 3718709 | 3718709 | 836647 | 262779 | 2619283
62 |  | Barton Hills Elementary | 873112 | 7037 | 552138 | 559175 | 323377 | 30278 | 205520
63 |  | Becker Elementary | 872038 | 0 | 700760 | 700760 | 374379 | 59042 | 267339
64 |  | Bedichek Middle School | 3961000 | 0 | 3098714 | 3098714 | 836141 | 461817 | 1800756
65 |  | Blackshear Elementary | 4111832 | 14616 | 3313549 | 3328165 | 2323951 | 178075 | 826139
66 |  | Blanton Elementary | 5168915 | 24700 | 3537431 | 3562131 | 2389811 | 359453 | 812867
67 |  | Blazier Elementary K-3 | 545028 | 0 | 325004 | 325004 | 225316 | 14882 | 84806
68 |  | Boone Elementary | 3001425 | 0 | 1888622 | 1888622 | 310450 | 134722 | 1443450
69 |  | Bowie High School | 24755800 | 0 | 16408149 | 16408149 | 10914079 | 1816618 | 3677452
70 |  | Bryker Woods Elementary | 5846143 | 0 | 4362578 | 4362578 | 464364 | 188114 | 3710100
71 |  | Campbell Elementary | 1184635 | 0 | 719518 | 719518 | 207896 | 5804 | 505818
72 |  | Casey Elementary | 6112001 | 0 | 4029455 | 4029455 | 2617196 | 1164589 | 247670
73 |  | Clayton Elementary | 2118238 | 0 | 998840 | 998840 | 232510 | 65514 | 700816
74 |  | Clifton Center | 13000228 | 0 | 9985068 | 9985068 | 1890344 | 7464752 | 629972
75 |  | Covington Middle School | 22933488 | 0 | 17605870 | 17605870 | 537356 | 510788 | 16557726
76 |  | Cowan Elementary | 832997 | 0 | 390063 | 390063 | 322437 | 46959 | 20667
77 |  | Cunningham Elementary | 1971219 | 0 | 1229779 | 1229779 | 211479 | 52651 | 965649
78 |  | Davis Elementary | 6198740 | 0 | 3781310 | 3781310 | 642271 | 39874 | 3099165
79 |  | Dawson Elementary | 1277142 | 0 | 675803 | 675803 | 150659 | 18171 | 506973
80 |  | Galindo Elementary | 10510069 | 0 | 5782340 | 5782340 | 760449 | 303762 | 4718129
81 |  | Garcia YMLA | 4583246 | 25000 | 2079457 | 2104457 | 561834 | 224805 | 1317818
82 |  | Garza Independence High School | 2603309 | 0 | 1401156 | 1401156 | 501424 | 133647 | 766085
83 |  | Gorzycki Middle School | 2283262 | 0 | 956270 | 956270 | 200936 | 20795 | 734539
84 |  | Graham Elementary | 12499396 | 0 | 8970763 | 8970763 | 252827 | 3336 | 8714600
85 |  | Guerrero Thompson Elementary | 2480674 | 0 | 1503421 | 1503421 | 156896 | 310549 | 1035976
86 |  | Gullett Elementary | 2849758 | 0 | 847367 | 847367 | 531899 | 32637 | 282831
87 |  | Hart Elementary | 3678230 | 0 | 2852075 | 2852075 | 315722 | 96834 | 2439519
88 |  | Highland Park Elementary | 13219341 | 0 | 8748195 | 8748195 | 236254 | 25881 | 8486060
89 |  | Jordan Elementary | 5000362 | 0 | 4029136 | 4029136 | 413384 | 111118 | 3504634
90 |  | Joslin Elementary | 3434917 | 640 | 1787086 | 1787726 | 551235 | 287988 | 948503
91 |  | Kealing Middle School | 3429176 | 0 | 2592262 | 2592262 | 200679 | 4595 | 2386988
92 |  | Kiker Elementary | 1554112 | 0 | 1052644 | 1052644 | 189316 | 77165 | 786163
93 |  | Kocurek Elementary | 1780765 | 0 | 1349918 | 1349918 | 322422 | 23825 | 1003671
94 |  | Lamar Middle School | 1048408 | 0 | 1283347 | 1283347 | 680709 | 48628 | 554010
95 |  | Lee Elementary | 519760 | 0 | 325323 | 325323 | 201746 | 5652 | 117925
96 |  | Lively Middle School | 3179267 | 10000 | 1584040 | 1594040 | 919695 | 136744 | 537601
97 |  | Maplewood Elementary | 987019 | 0 | 899047 | 899047 | 395631 | 102773 | 400643
98 |  | Mathews Elementary | 558601 | 4042 | 538374 | 542416 | 176000 | 16436 | 349980
99 |  | McBee Elementary | 6183100 | 0 | 3552858 | 3552858 | 1129145 | 406230 | 2017483
100 |  | Mendez Middle School | 19175133 | 0 | 15235801 | 15235801 | 9358143 | 1747180 | 4130478
101 |  | Metz Facility | 0 | 0 | 774846 | 774846 | 0 | 0 | 774846
102 |  | Mills Elementary | 1193142 | 0 | 1795915 | 1795915 | 940850 | 467248 | 387817
103 |  | Ortega Elementary | 13025058 | 25000 | 9352065 | 9377065 | 200364 | 356964 | 8819737
104 |  | Overton Elementary | 1757293 | 80000 | 1189719 | 1269719 | 168805 | 68645 | 1032269
105 |  | Padron Elementary | 2471987 | 0 | 1293433 | 1293433 | 319945 | 29533 | 943955
106 |  | Palm Elementary | 4718272 | -156784 | 2332615 | 2175831 | 729637 | 33678 | 1412516
107 |  | Paredes Middle School | 5082573 | 0 | 3985248 | 3985248 | 201462 | 33464 | 3750322
108 |  | Patton Elementary | 4284708 | 0 | 2001895 | 2001895 | 259622 | 261902 | 1480371
109 |  | Perez Elementary | 999682 | 0 | 949986 | 949986 | 235567 | 14995 | 699424
110 |  | Pickle Elementary | 4937116 | 0 | 1820604 | 1820604 | 243067 | 106492 | 1471045
111 |  | Pillow Elementary | 2474897 | 0 | 586252 | 586252 | 229794 | 23860 | 332598
112 |  | Pleasant Hill Elementary | 2167098 | 0 | 998217 | 998217 | 198952 | 32376 | 766889
113 |  | Reilly Elementary | 4950107 | 0 | 3623095 | 3623095 | 448476 | 289154 | 2885465
114 |  | Ridgetop Elementary | 5215209 | 0 | 3766825 | 3766825 | 223537 | 129422 | 3413866
115 |  | Rodriguez Elementary | 5634979 | 0 | 2583936 | 2583936 | 1581687 | 627409 | 374840
116 |  | Small Middle School | 244550 | 0 | 260319 | 260319 | 249250 | 6312 | 4757
117 |  | St. Elmo Elementary | 5897572 | 0 | 2517504 | 2517504 | 189813 | 8436 | 2319255
118 |  | Summitt Elementary | 983495 | 0 | 993609 | 993609 | 555615 | 29326 | 408668
119 |  | Sunset Valley Elementary | 1250600 | 0 | 725188 | 725188 | 282705 | 60445 | 382038
120 |  | Travis Early College High School | 0 | 0 | 52945 | 52945 | 49815 | 0 | 3130
121 |  | Travis Heights Elementary | 2999930 | 0 | 1931573 | 1931573 | 432284 | 113822 | 1385467
122 |  | Uphaus Early Childhood Center | 715942 | 0 | 442985 | 442985 | 76646 | 3054 | 363285
123 |  | Walnut Creek Elementary | 4040845 | 0 | 961626 | 961626 | 447254 | 34111 | 480261
124 |  | Webb Middle School | 12669976 | 0 | 7445172 | 7445172 | 436270 | 53320 | 6955582
125 |  | Widen Elementary | 6160033 | -31572 | 3682277 | 3650705 | 2492132 | 405036 | 753537
126 |  | Winn Montessori | 5846381 | -154625 | 3477848 | 3323223 | 189247 | 238306 | 2895670
127 |  | Zavala Elementary | 4232845 | 0 | 1800908 | 1800908 | 411880 | 485290 | 903738
128 |  | Zilker Elementary | 1064987 | 0 | 533107 | 533107 | 177031 | 23067 | 333009
129 |  | Print Shop Move | 0 | 0 | 57082 | 57082 | -8600 | 8600 | 57082
130 |  | Districtwide Secure Vestibules | 0 | 151946 | 22271827 | 22423773 | 1709384 | 2202729 | 18511660
131 |  | Subtotal Secure Vestibule: | 342735326 | 0 | 247156765 | 247156765 | 62068140 | 33159035 | 151929590
132 |  | Non Campus Projects:
133 |  | Bus Replacement Plan | 25736000 | 0 | 25249590 | 25249590 | 17809124 | 7010708 | 429758
134 |  | Athletic - Turf Fields | 0 | 0 | 50697990 | 50697990 | 26180619 | 19046833 | 5470538
135 |  | EWAS | 0 | 0 | 47500 | 47500 | 38220 | 9281 | -1
136 |  | Land for Future SE Elementary School | 5000000 | 0 | 4666285 | 4666285 | 4656283 | 9952 | 50
137 |  | Impervious Cover | 0 | 0 | 171122 | 171122 | 141063 | 46618 | -16559
138 |  | IRCA Professional Services | 0 | 0 | 2000000 | 2000000 | 806441 | 1117729 | 75830
139 |  | Food Services - Kitchen Equipment | 0 | 0 | 29209843 | 29209843 | 9807851 | 12773879 | 6628113
140 |  | Future SE HS Planning and Design | 800000 | 0 | 748880 | 748880 | 0 | 0 | 748880
141 |  | Planning and Design Studies | 2500000 | 0 | 2348750 | 2348750 | 694355 | 7445 | 1646950
142 |  | Dispersed Dining - Vending | 150000 | 0 | 147165 | 147165 | 0 | 0 | 147165
143 |  | Musical Instruments | 5000000 | 0 | 4905500 | 4905500 | 2308912 | 1315237 | 1281351
144 |  | Subtotal Non Campus Projects: | 39186000 | 0 | 120192625 | 120192625 | 62442868 | 41337682 | 16412075
145 |  | Undesignated:
146 |  | Doors and Locks Security Improvements | 5000000 | 0 | 7551500 | 7551500 | 3924523 | 3625277 | 1700
147 |  | Special Education Inclusion Improvements and Cameras | 15200000 | 0 | 13300720 | 13300720 | 228943 | 172368 | 12899409
148 |  | Furniture | 3500000 | 0 | 3289850 | 3289850 | 1571636 | 1809 | 1716405
149 |  | HVAC and Other Building Deficiencies | 25000000 | 0 | 16718271 | 16718271 | 3232781 | 647435 | 12838055
150 |  | Middle and High School Athletic Facility Repairs | 9800000 | 0 | 1382846 | 1382846 | 105504 | 111916 | 1165426
151 |  | Outdoor Learning Spaces and/or Activity Spaces | 4700000 | 0 | 3633287 | 3633287 | 2302764 | 303207 | 1027316
152 |  | Roofing | 9250000 | 0 | 6968454 | 6968454 | 1403211 | 586665 | 4978578
153 |  | Security Fencing | 5000000 | 0 | 13809702 | 13809702 | 11893557 | 1371042 | 545103
154 |  | Universal Design Improvements | 400000 | 0 | 1372440 | 1372440 | 151153 | 1186621 | 34666
155 |  | Subtotal Undesignated: | 77850000 | 0 | 68027070 | 68027070 | 24814072 | 8006340 | 35206658
156 |  | Subtotal Targeted Projects | 575333669 | 0 | 541573318 | 541573318 | 209681964 | 88751475 | 243139879
157 |  | Non Construction-Prop A:
158 |  | Program Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 |  | Program Management | 0 | 0 | 195515470 | 195515470 | 93649706 | 40547058 | 61318706
160 |  | Subtotal Non Construction-Prop A | 0 | 0 | 195515470 | 195515470 | 93649706 | 40547058 | 61318706
161 |  | Total Proposition A | 2316024940 | 0 | 2316025000 | 2316025000 | 814693185 | 881720313 | 619611502
162 |  | Proposition B
163 |  | Campus Technology:
164 |  | Akins Early College High School | 2161566 | 0 | 0 | 0 | 0 | 0 | 0
165 |  | Allison Elementary | 226394 | 0 | 0 | 0 | 0 | 0 | 0
166 |  | Anderson High School | 1831548 | 0 | 0 | 0 | 0 | 0 | 0
167 |  | Andrews Elementary | 177384 | 0 | 0 | 0 | 0 | 0 | 0
168 |  | Anita Coy (ALC) | 102041 | 0 | 0 | 0 | 0 | 0 | 0
169 |  | Ann Richards SYWL | 866000 | 0 | 0 | 0 | 0 | 0 | 0
170 |  | Austin High School | 1922353 | 0 | 0 | 0 | 0 | 0 | 0
171 |  | Bailey Middle School | 809891 | 0 | 0 | 0 | 0 | 0 | 0
172 |  | Baldwin Elementary | 612039 | 0 | 0 | 0 | 0 | 0 | 0
173 |  | Baranoff Elementary | 738300 | 0 | 0 | 0 | 0 | 0 | 0
174 |  | Barrington Elementary | 171843 | 0 | 0 | 0 | 0 | 0 | 0
175 |  | Barton Hills Elementary | 440888 | 0 | 0 | 0 | 0 | 0 | 0
176 |  | Bear Creek Elementary | 458243 | 0 | 0 | 0 | 0 | 0 | 0
177 |  | Becker Elementary | 500962 | 0 | 0 | 0 | 0 | 0 | 0
178 |  | Bedichek Middle School | 726000 | 0 | 0 | 0 | 0 | 0 | 0
179 |  | Blackshear Elementary | 377168 | 0 | 0 | 0 | 0 | 0 | 0
180 |  | Blanton Elementary | 588085 | 0 | 0 | 0 | 0 | 0 | 0
181 |  | Blazier Elementary 4-6 | 920000 | 0 | 0 | 0 | 0 | 0 | 0
182 |  | Blazier Elementary K-3 | 223972 | 0 | 0 | 0 | 0 | 0 | 0
183 |  | Boone Elementary | 513575 | 0 | 0 | 0 | 0 | 0 | 0
184 |  | Bowie High School | 2233200 | 0 | 0 | 0 | 0 | 0 | 0
185 |  | Brentwood Elementary | 589000 | 0 | 0 | 0 | 0 | 0 | 0
186 |  | Brown Elementary | 1694 | 0 | 0 | 0 | 0 | 0 | 0
187 |  | Bryker Woods Elementary | 402857 | 0 | 0 | 0 | 0 | 0 | 0
188 |  | Burnet Middle School | 539166 | 0 | 0 | 0 | 0 | 0 | 0
189 |  | Campbell Elementary | 333365 | 0 | 0 | 0 | 0 | 0 | 0
190 |  | Casey Elementary | 509999 | 0 | 0 | 0 | 0 | 0 | 0
191 |  | Casis Elementary | 592000 | 0 | 0 | 0 | 0 | 0 | 0
192 |  | Clayton Elementary | 638762 | 0 | 0 | 0 | 0 | 0 | 0
193 |  | Clifton Center | 244772 | 0 | 0 | 0 | 0 | 0 | 0
194 |  | Cook Elementary | 477575 | 0 | 0 | 0 | 0 | 0 | 0
195 |  | Covington Middle School | 697512 | 0 | 0 | 0 | 0 | 0 | 0
196 |  | Cowan Elementary | 540003 | 0 | 0 | 0 | 0 | 0 | 0
197 |  | Crockett Early College High School | 1421782 | 0 | 0 | 0 | 0 | 0 | 0
198 |  | Cunningham Elementary | 453781 | 0 | 0 | 0 | 0 | 0 | 0
199 |  | Davis Elementary | 597260 | 0 | 0 | 0 | 0 | 0 | 0
200 |  | Dawson Elementary | 382858 | 0 | 0 | 0 | 0 | 0 | 0
201 |  | Dobie Middle School | 656225 | 0 | 0 | 0 | 0 | 0 | 0
202 |  | Doss Elementary | 713000 | 0 | 0 | 0 | 0 | 0 | 0
203 |  | Eastside Early College High School | 729143 | 0 | 0 | 0 | 0 | 0 | 0
204 |  | Galindo Elementary | 493931 | 0 | 0 | 0 | 0 | 0 | 0
205 |  | Garcia YMLA | 414754 | 0 | 0 | 0 | 0 | 0 | 0
206 |  | Garza Independence High School | 337691 | 0 | 0 | 0 | 0 | 0 | 0
207 |  | Gorzycki Middle School | 1137738 | 0 | 0 | 0 | 0 | 0 | 0
208 |  | Govalle Elementary | 444897 | 0 | 0 | 0 | 0 | 0 | 0
209 |  | Graham Elementary | 486604 | 0 | 0 | 0 | 0 | 0 | 0
210 |  | Guerrero Thompson Elementary | 534326 | 0 | 0 | 0 | 0 | 0 | 0
211 |  | Gullett Elementary | 562242 | 0 | 0 | 0 | 0 | 0 | 0
212 |  | Harris Elementary | 186310 | 0 | 0 | 0 | 0 | 0 | 0
213 |  | Hart Elementary | 531770 | 0 | 0 | 0 | 0 | 0 | 0
214 |  | Highland Park Elementary | 589659 | 0 | 0 | 0 | 0 | 0 | 0
215 |  | Hill Elementary | 715379 | 0 | 0 | 0 | 0 | 0 | 0
216 |  | Houston Elementary | 275672 | 0 | 0 | 0 | 0 | 0 | 0
217 |  | Jordan Elementary | 532638 | 0 | 0 | 0 | 0 | 0 | 0
218 |  | Joslin Elementary | 394083 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Kealing Middle School | 1138824 | 0 | 0 | 0 | 0 | 0 | 0
220 |  | Kiker Elementary | 676888 | 0 | 0 | 0 | 0 | 0 | 0
221 |  | Kocurek Elementary | 526235 | 0 | 0 | 0 | 0 | 0 | 0
222 |  | Lamar Middle School | 1073592 | 0 | 0 | 0 | 0 | 0 | 0
223 |  | Langford Elementary | 278905 | 0 | 0 | 0 | 0 | 0 | 0
224 |  | LBJ Early College High School | 842578 | 0 | 0 | 0 | 0 | 0 | 0
225 |  | Lee Elementary | 505240 | 0 | 0 | 0 | 0 | 0 | 0
226 |  | Liberal Arts and Science Academy High School | 1249516 | 0 | 0 | 0 | 0 | 0 | 0
227 |  | Linder Elementary | 279261 | 0 | 0 | 0 | 0 | 0 | 0
228 |  | Lively Middle School | 1061733 | 0 | 0 | 0 | 0 | 0 | 0
229 |  | Maplewood Elementary | 459981 | 0 | 0 | 0 | 0 | 0 | 0
230 |  | Martin Middle School | 446070 | 0 | 0 | 0 | 0 | 0 | 0
231 |  | Mathews Elementary | 430399 | 0 | 0 | 0 | 0 | 0 | 0
232 |  | McBee Elementary | 427900 | 0 | 0 | 0 | 0 | 0 | 0
233 |  | McCallum High School | 1549475 | 0 | 0 | 0 | 0 | 0 | 0
234 |  | Menchaca Elementary | 658000 | 0 | 0 | 0 | 0 | 0 | 0
235 |  | Mendez Middle School | 376867 | 0 | 0 | 0 | 0 | 0 | 0
236 |  | Mills Elementary | 688858 | 0 | 0 | 0 | 0 | 0 | 0
237 |  | Murchison Middle School | 1125623 | 0 | 0 | 0 | 0 | 0 | 0
238 |  | Navarro Early College High School | 1446983 | 0 | 0 | 0 | 0 | 0 | 0
239 |  | Norman-Sims Elementary | 382361 | 0 | 0 | 0 | 0 | 0 | 0
240 |  | Northeast ECHS / International High School | 1169653 | 0 | 0 | 0 | 0 | 0 | 0
241 |  | O Henry Middle School | 768774 | 0 | 0 | 0 | 0 | 0 | 0
242 |  | Oak Hill Elementary | 613492 | 0 | 0 | 0 | 0 | 0 | 0
243 |  | Oak Springs Elementary | 122082 | 0 | 0 | 0 | 0 | 0 | 0
244 |  | Odom Elementary | 428870 | 0 | 0 | 0 | 0 | 0 | 0
245 |  | Ortega Elementary | 382942 | 0 | 0 | 0 | 0 | 0 | 0
246 |  | Overton Elementary | 472707 | 0 | 0 | 0 | 0 | 0 | 0
247 |  | Padron Elementary | 547013 | 0 | 0 | 0 | 0 | 0 | 0
248 |  | Palm Elementary | 439728 | 0 | 0 | 0 | 0 | 0 | 0
249 |  | Paredes Middle School | 706427 | 0 | 0 | 0 | 0 | 0 | 0
250 |  | Patton Elementary | 686292 | 0 | 0 | 0 | 0 | 0 | 0
251 |  | Pecan Springs Elementary | 157188 | 0 | 0 | 0 | 0 | 0 | 0
252 |  | Perez Elementary | 497318 | 0 | 0 | 0 | 0 | 0 | 0
253 |  | Pickle Elementary | 418884 | 0 | 0 | 0 | 0 | 0 | 0
254 |  | Pillow Elementary | 468103 | 0 | 0 | 0 | 0 | 0 | 0
255 |  | Pleasant Hill Elementary | 451902 | 0 | 0 | 0 | 0 | 0 | 0
256 |  | Reilly Elementary | 409893 | 0 | 0 | 0 | 0 | 0 | 0
257 |  | Ridgetop Elementary | 437791 | 0 | 0 | 0 | 0 | 0 | 0
258 |  | Rodriguez Elementary | 453021 | 0 | 0 | 0 | 0 | 0 | 0
259 |  | Rosedale School | 371000 | 0 | 0 | 0 | 0 | 0 | 0
260 |  | Sadler Means YWLA | 227158 | 0 | 0 | 0 | 0 | 0 | 0
261 |  | Sanchez Elementary | 504262 | 0 | 0 | 0 | 0 | 0 | 0
262 |  | Small Middle School | 1102450 | 0 | 0 | 0 | 0 | 0 | 0
263 |  | St. Elmo Elementary | 406428 | 0 | 0 | 0 | 0 | 0 | 0
264 |  | Summitt Elementary | 676505 | 0 | 0 | 0 | 0 | 0 | 0
265 |  | Sunset Valley Elementary | 491400 | 0 | 0 | 0 | 0 | 0 | 0
266 |  | Travis Early College High School | 754038 | 0 | 0 | 0 | 0 | 0 | 0
267 |  | Travis Heights Elementary | 542070 | 0 | 0 | 0 | 0 | 0 | 0
268 |  | Uphaus Early Childhood Center | 397058 | 0 | 0 | 0 | 0 | 0 | 0
269 |  | Walnut Creek Elementary | 529155 | 0 | 0 | 0 | 0 | 0 | 0
270 |  | Webb Middle School | 640024 | 0 | 0 | 0 | 0 | 0 | 0
271 |  | Widen Elementary | 449967 | 0 | 0 | 0 | 0 | 0 | 0
272 |  | Williams Elementary | 452981 | 0 | 0 | 0 | 0 | 0 | 0
273 |  | Winn Montessori | 369619 | 0 | 0 | 0 | 0 | 0 | 0
274 |  | Wooldridge Elementary | 231845 | 0 | 0 | 0 | 0 | 0 | 0
275 |  | Wooten Elementary | 297663 | 0 | 0 | 0 | 0 | 0 | 0
276 |  | Zavala Elementary | 395155 | 0 | 0 | 0 | 0 | 0 | 0
277 |  | Zilker Elementary | 500013 | 0 | 0 | 0 | 0 | 0 | 0
278 |  | Subtotal Undesignated: | 69356060 | 0 | 0 | 0 | 0 | 0 | 0
279 |  | Districtwide:
280 |  | Districtwide Network Upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 0
281 |  | Staff/Student Devices and Equipment | 6185000 | 0 | 75541000 | 75541000 | 34953003 | 4837088 | 35750909
282 |  | Subtotal Districtwide: | 6185000 | 0 | 75541000 | 75541000 | 34953003 | 4837088 | 35750909
283 |  | Total Proposition B | 75541060 | 0 | 75541000 | 75541000 | 34953003 | 4837088 | 35750909
284 |  | Proposition C
285 |  | Stadiums & Athletic Complexes:
286 |  | Burger Athletic Complex | 4767000 | 0 | 3676366 | 3676366 | 0 | 299067 | 3377299
287 |  | Delco Activity Center | 15000000 | 0 | 11340709 | 11340709 | 415202 | 715181 | 10210326
288 |  | Nelson Field | 25000000 | 0 | 19301337 | 19301337 | 499983 | 1212198 | 17589156
289 |  | Noack Sports Complex | 2667000 | 0 | 2054636 | 2054636 | 0 | 186106 | 1868530
290 |  | Subtotal Undesignated: | 47434000 | 0 | 36373048 | 36373048 | 915185 | 2412552 | 33045311
291 |  | Non Construction-Prop C:
292 |  | Program Contingency | 0 | 0 | 2834978 | 2834978 | 0 | 0 | 2834978
293 |  | Program Management | 0 | 0 | 8225974 | 8225974 | 28691 | 0 | 8197283
294 |  | Subtotal Non Construction-Prop C | 0 | 0 | 11060952 | 11060952 | 28691 | 0 | 11032261
295 |  | Total Proposition C | 47434000 | 0 | 47434000 | 47434000 | 943876 | 2412552 | 44077572
296 |  | 2022 Bond Total Amount | 2439000000 | 0 | 2439000000 | 2439000000 | 850590064 | 888969953 | 699439983
Notes:
All numbers are as of January 31, 2026.
Numbers may not add due to rounding.
2022 Bond Interest Projects
|  | Projects | Initial | BUDGET AMENDMENTS | Budget a/o December 31, 2025 | Budget a/o January 31, 2026 | Actuals | Commitments | Balance
Proposition A
|  | Police Allotment - Vehicles/Equipment/Accessories | 0 | 0 | 7652744 | 7652744 | 7055972.74 | 5549.09 | 591222.17
|  | HVAC Controls | 0 | 0 | 7100000 | 7100000 | 0 | 0 | 7100000
|  | Travis ECHS GMP #5 (230014) | 0 | 0 | 42529070 | 42529070 | 5383061.95 | 29851673.03 | 7294335.02
|  | Total Proposition A | 0 | 0 | 57281814 | 57281814 | 12439034.69 | 29857222.12 | 14985557.19
Proposition B
|  | Allovue | 0 | 0 | 411750 | 411750 | 411750 | 0 | 0
|  | Technology Allotment - | 0 | 0 | 83078 | 83078 | 75366 | 7712 | 0
|  | Total Proposition B | 0 | 0 | 494828 | 494828 | 487116 | 7712 | 0
Proposition C
|  | House Park (#210034) | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Proposition C | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2022 Bond Interest Total Amount | 0 | 0 | 57776642 | 57776642 | 12926150.69 | 29864934.12 | 14985557.19
Note: Interest Budget approved for House Park project #210034; however, it will not be allocated until the end of February ($5,960,742).